## Sheet1
Day | Total Time (Min) | Comments | Session No.
2023-09-18 | 83 | Made the basic UI and setup the base design. Can be found in ui_build branch. | 1
2023-09-19 | 62 | Setup FireBase, Created Landing Screen and designed CustomButton and ErrorScreen (Basic Scaffold) | 1
2023-09-20 | 82 | Create Login Screen with Country Picker and setup Named Routes in main.dart and create a router by the name router.dart | 1
2023-09-20 | 36 | Created AuthRepository(Phone Login), OTP Screen foundation led up, Updated router.dart for OTPScreen to get verificationId as argument. Created utils.dart with Snackbar | 2
2023-09-20 | 38 | Configured AuthController Provider and AuthRepositoryProvider and modified main.dart. Setup Business login in sendPhoneNumber() using ref.read() | 3
2023-09-20 | 85 | Added SHA - 1 fingerprint on firebase console. Created OTP Screen and added OTP business logic and verification WORKS! Added route, modified auth repo and controller. | 4